## Mentee Training Plan AutoQC to
Phase | Duration | Theme | Key Activities & Learning Objectives | deliverables | Success Metrics (KPIs)
Month 1 | Week 1-2 | Azure ML Foundation & Clean Code | • Refactor existing VLM/Qwen scripts into modular Python packages.• Implement strict linting (Ruff/Pylint) and type checking (mypy).• Set up Azure ML Workspace, Compute Instances, and Data Assets for BDD. | • Refactored autoqc-core repository.• requirements.txt / conda.yaml finalized.• Raw BDD data registered in Azure Data Lake. | • Code Quality Score > 8/10.• Zero linting errors in main branch.
| Week 3-4 | Reproducibility & Experiment Tracking | • Migrate ad-hoc VLM runs to Azure ML Jobs (Command Jobs).• Implement MLflow for logging metrics (precision/recall on BDD) and params.• Containerize the environment (Docker). | • Dockerfile for the AutoQC environment.• First successful Azure ML training/inference run logged in MLflow. | • 100% of experiments tracked centrally (no local logs).
Month 2 | Week 5-6 | CI/CD for ML (The MLOps Loop) | • Build CI pipeline (GitHub Actions/Azure DevOps) to run unit tests on PRs.• Automate the build and registration of the Docker image.• Create a "Model Registry" workflow for the Qwen-based models. | • ci.yaml pipeline file.• Automated Unit Test report generation.• Versioned models in Azure ML Registry. | • PR Build time < 10 mins.• Test coverage > 70%.
| Week 7-8 | Pipeline Orchestration | • Create an Azure ML Pipeline (DAG) linking Data Prep -> Inference -> Evaluation.• Automate the pipeline trigger based on new data arrival or schedule. | • End-to-End Azure ML Pipeline script.• Scheduled nightly run of AutoQC on new data samples. | • Automated pipeline runs successfully without manual intervention.
Month 3 | Week 9-10 | Performance & Optimization | • Profile the VLM inference code; optimize for latency/throughput.• Implement batch processing for large-scale BDD data evaluation.• Cost optimization (selecting right VM sizes, spot instances). | • Performance benchmark report (Time per frame).• Cost analysis report. | • Inference speedup by X%.• Cloud cost kept within $Y budget.
| Week 11-12 | Data-Driven Feedback & Review | • Dashboarding: Visualize AutoQC results (Power BI or Custom App).• Handling Data Drift: Detect if BDD data distribution changes.• Final Project Presentation & Knowledge Transfer. | • Operational Dashboard.• Final "Production Ready" AutoQC Release.• Handover documentation. | • Dashboard adoption by Data Team.• System stability > 99%.